## Jira Lab Plan
Agenda
1 | Creating Jira Site | 5
2 | Creating Project | 5
3 | Creating Board | 5
4 | Configuring Workflows and Columns | 5
5 | Create Version | 5
6 | Creating Epic | 5
7 | Creating Story | 5
8 | Creating Task | 5
9 | Creating Bug | 5
10 | Creating Subtask | 5
11 | Starting a Sprint | 10
13 | Transitioning Issues | 5
14 | Finishing an Active Sprint | 5
15 | Using Reports | 5
75

## Create Jira Site
How to set up Jira Software Cloud
HOW TO | Step 1 | Go to the Atlassian website: https://www.atlassian.com/
| Step 2 | Select the Jira Software option
| Step 3 | Decide which plan is right for you
| Step 4 | Create an account
| Step 5 | Personalize your experience
| Step 6 | Invite your teammates
| Step 7 | Recommend a project
| Step 8 | Choose a classic template
| Step 9 | Create project
| Step 10 | That's it, your site was created

## Create Project & Board
Create Project
HOW TO | Step 1 | Choose the Jira icon ( or ) > Projects.
| Step 2 | Select Create project (top right).
| Step 3 | Choose Classic project.
| Step 4 | Give your project a name.
| Step 5 | Change Template.
| Step 6 | Select Create.
Try it
TRY IT | Step 1 | Create a new Scrum Project
| Step 2 | Name the project Used Car Trader
| Step 3 | Accept the key Jira generates
| Step 4 | View Project Settings > Details and confirm that you are the project lead.

## Configure Workflows and Columns
Configuring Workflows and Columns
HOW TO | Step 1 | Go to your board, then select more (•••) > Board settings.
| Step 2 | Click the Columns tab.
| Step 3 | Click the Add status button.
Try it
TRY IT | Step 1 | Add a new column to your workflow, named QA.
| Step 2 | Move the new column just after the "Done" column.
| Step 3 | Move the QA column back to its original location, before "Done"

## Create Version
Create Version
HOW TO | Step 1 | Click on "VERSIONS" from the left-hand panel on the backlog screen.
| Step 2 | Click on the "Create Version" link in the expanded Versions panel.
| Step 3 | Provide a Name for the version.
| Step 4 | Provide a Description.
| Step 5 | Edit Start and Release Date and click on the Create button.
Try it
TRY IT | Step 1 | Create a new Version
| Step 2 | Name the Version UsedCar_V1.1
| Step 3 | Edit Start Date today and Release Date 1 months later

## Create Epic
Create Epic
HOW TO | Step 1 | Click on "EPICS" from the left-hand panel on the backlog screen.
| Step 2 | Click on the "Create Epic" link in the expanded Epics panel.
| Step 3 | Provide a short name to identify the epic.
| Step 4 | Provide a Summary.
| Step 5 | Fill in the additional fields and click on the Create button.
Try it
TRY IT | Step 1 | Create a new Epic
| Step 2 | Name the epic Used Car Trader website design
| Step 3 | Write a summary For a used car website, the target is to meet the wishes of users.

## Create Story
Create Story
HOW TO | Step 1 | Click on "+" button from the global navigation bar or press the C key.
| Step 2 | Select the Issue Type as Story.
| Step 3 | Provide a Summary.
| Step 4 | Fill in the additional fields and click on the Create button.
Try it
TRY IT | Step 1 | Create at least 2 story (Use sample stories below).
| Step 2 | Provide a Summary.
| Step 3 | Add priority.
| Step 4 | Assign user to story.
| Step 5 | Enter story point.
| Step 6 | Use the Create Another option when creating the second issue.
SAMPLE STORIES | ID | Story Summary | Story Points | Priority
| 1 | As an unregistered user, I want to view listed cars So that I can see the features and the prices of cars. | 5 | High
| 2 | As an unregistered user, I want to register on the website, So that I can buy the listed cars and sell my own car. | 3 | High
| 3 | As a registered user, I want to save my cars on the website, So that I can get an instant valuation. | 5 | Medium
| 4 | As a registered user, I want to save the favoritte adverts, So that I can easily return to these adverts later. | 3 | Medium
| 5 | As a registered user, I want to save my searches on the website, So that I can get notifications that match my search criteria. | 5 | Highest
| 6 | As a registered user, I want to create advertisement, So that I can sell my own car. | 8 | High
| 7 | As a registered user, I want to save my personal and contact information, So that buyers and sellers can contact me. | 8 | High
| 8 | As a registered user, I want to send message to sellers, So that I can chat with sellers. | 5 | Medium

## Create Task
Create Task
HOW TO | Step 1 | Click on "+" button from the global navigation bar or press the C key.
| Step 2 | Select the Issue Type as Task.
| Step 3 | Provide a Summary.
| Step 4 | Fill in the additional fields and click on the Create button.
Try it
TRY IT | Step 1 | Create a task (Use sample tasks below).
| Step 2 | Provide a Summary.
| Step 3 | Add priority.
| Step 4 | Assign user to Task.
| Step 5 | Attach a file.
SAMPLE TASKS | ID | Summary | Priority
| 1 | Redesign a single web page | High
| 2 | Create a new logo | High
| 3 | Perform usability testing | Medium

## Create Subtask
Create Subtask
HOW TO | Step 1 | Click on an issue where you want subtasks to be created.
| Step 2 | From the dialog box, click Create subtask.
| Step 3 | Add a summary to your subtask and click "Create" button.
| Step 4 | Click on a subtask that you have created and you can fill in the fields.
Try it
TRY IT | Step 1 | Create at least 2 subtasks for both a story and a task (Use sample subtasks below).
| Step 2 | Provide a Summary and a Description.
| Step 3 | Add priority.
| Step 4 | Assign user to Subtask.
| Step 5 | Add a web link. (e.g., https://www.atlassian.com/software/jira)
SAMPLE TASKS | ID | Summary | Priority
| 1 | Reviewing User Stories | High
| 2 | Creating Test cases | High
| 3 | Reviewing Test cases | Medium
| 4 | Setting Up Test Environment | High
| 5 | Creating Test data | High
| 6 | Executing Manual Tests | Medium
| 7 | Automation Setup | High
| 8 | Automation Design | High
| 9 | Automating Test Cases | Medium
| 10 | Retesting Bugs | High
| 11 | Regression Testing | High
| 12 | Demo User Story | Medium

## Create Bug
Create Bug
HOW TO | Step 1 | Click on "+" button from the global navigation bar or press the C key.
| Step 2 | Select the Issue Type as Task.
| Step 3 | Provide a Summary.
| Step 4 | Fill in the additional fields and click on the Create button.
Try it
TRY IT | Step 1 | Create a bug (Use sample bugs below).
| Step 2 | Provide a Summary and a Description.
| Step 3 | Add priority.
| Step 4 | Assign user to Bug.
| Step 5 | Add a comment to Bug and mention someone.
SAMPLE BUGS | ID | Summary | Bug Description | Priority
| 1 | When clicking on registration, website crashes. | Website crashes each time when clicking onregistration. Using the 10.28.99 build on a Win NT 4.0 (Service Pack 5) system. | Highest
| 2 | Unregistered users are not able to view the prices of the cars. | When in unregistered mode, being able to see all the feaures of the cars, but not able to view the prices. Need to fix this bug. | Highest

## Starting a Sprint
Starting a Sprint
HOW TO | Step 1 | Create a sprint by clicking on the "Create Sprint" button from the backlog.
| Step 2 | Add issues from the product backlog into the sprint backlog by dragging and dropping.
| Step 3 | After you add all the issues you plan in the sprint, click on the "Start Sprint" button.
| Step 4 | Fill in the fields in the dialogue box.
Try it
TRY IT | Step 1 | Go to Backlog, and create a sprint
| Step 2 | Put the issues in priority order
| Step 3 | Drag the issues into the sprint
| Step 4 | Start the sprint and name it, "Initial Sprint". Make the duration 2 weeks.
| Step 5 | Change to the Active Sprints view.

## Transitioning Issues
Try it
TRY IT | Step 1 | In the Active Sprints view, transition both of your tasks and subtasks ton In Progress
| Step 2 | Transition one of tasks to QA
| Step 3 | Transition your stories to In Progress
| Step 4 | Log Time on your stories.

## Finish Sprint
Finishing an Active Sprint
HOW TO | Step 1 | Select "Active Sprint" from your board and click on the "Complete Sprint" button.
| Step 2 | Click on the "Complete" button to complete the sprint.
Try it
TRY IT | Step 1 | Complete the "Initial Sprint" you created.
| Step 2 | Move incomplete issues to a future sprint that's already created.

## Use Reports
Using Reports
HOW TO | 1 | Since the project you created has so little data, reporting on that project will not be useful.
| 2 | Just try to understand Burndown Chart, Sprint Report, and Velocity Chart.